BUy Asbl DUSABIKANE

September 2021

Project Summary

| Project title | Project of empowerment of women supervised by the Asbl DUSABIKANE/AKARARO. |
| --- | --- |
| Duration of the project | 12months From 01/01/2022 to 31/12/2022 |
| Project objectives | Objective: Economic empowerment of women through income-generating activities. |
| Target Group(s) | 187 women supported by DUSABIKANE/AKARARO |
| Final recipients | There are 1122 household members of the 187 women by DUSABIKANE/AKARARO |
| Expected results | Result 0: Project management, coordination and operation are ensured; Result 1: complete flour made from wheat and soybean maize is available, Result 2: A shop for the marketing of consumer goods and processed products (porridge and maize flour) is opened, Result 3: A pig cow-calf centre of the cooperative is set up, Result 4: A small artisanal banana processing unit is installed. |
| Beneficiary organisation | AKARARO Asbl |
| Implementing organizations | AKARARO Asbl |
| Budget | 78 886 Euros |
| Contact person | Ernest SENDAZIRASA ; Tel : +257 79 963 149 E-mail address : kizerwamirazi@gmail.com |

- DESCRIPTION

- Project title: Project of empowerment of women supervised by the Asbl DUSABIKANE/AKARARO.

- Location of the project: Municipality Mbuye of the Muramvya Province.

- Project Summary

Since 2017 DUSABIKANE/AKARARO has supported 187 women; the support already provided to these brave women has enabled these women to:

• Improve their food security (more than 1 meal a day) through improved agricultural production (corn, beans, wheat) and pig farming,

• Better social consideration as they contribute to the good of their respective families,

• Send their children to school, paying school fees,

• Provide health coverage for their families,

For the moment, they need more than ever to be independent in their economic and social life.

- Context

The development of a country goes through different channels, either from national policies or through individual or collective investments. When people come together to create development groups or associations, we move on to the development of a large number of people. The association DUSABIKANE, in collaboration with the Akararo centre, accompanies 179 households of all married women, including 28 young people (women under 35 years) and 28 widows all responsible for households. This project aims at the economic and social empowerment of the members of this cooperative.

- OPERATIONAL FRAMEWORK

DUSABIKANE has a partnership with a local NGO AKARARO, who works in the sector of training of young people and women who have dropped out of school due to financial problems or unwanted pregnancies has established since 2014 a training center in Kivoga in Mbuye province Muramvya. We have already trained more than 100 young people in sewing trades, carpentry, mechanical masonry, computer science, bakery, culinary arts, photography, welding and electricity. Apart from this youth training activity, we support 9 women’s organizations in the development activities of AGRS (Income Generating Activities) that have just ended with the end of 2019. It is in this context that we want to go up with supporting these women by:

- The manufacture of whole meal for porridge and corn flour.

This will be done as follows:

O Installation of a cyclone mill (already purchased): its shelter is built but it is necessary to buy the missing parts (electrical cables, belts, base, etc.),

o Training of users on the use and maintenance of the mill,

o The creation of working capital for the acquisition of grain to run this unit,

o The construction of a storage shed for grain corn and flour before it is placed on the market,

o The intensification of maize, wheat, sorghum, sesame, and livestock crops as ingredients of whole meal.

o Training of women to adopt the best meal formulas.

Here the external support will focus on:

• Seeds selected for the first cycle (start-up),

• Construction of the storage shed for crops and processed products.

- Opening of a food shop.

The objectives are to:

o Selling maize and wheat flour and porridge on the squares: improving the food security of local households, including those of members,

o Have consumer goods close by.

- Construction of a pigsty as a cow-calf centre for members and others

The following steps are planned:

a.  Construction of a pig barn,

b.  Supply of pigs (with at least 50 starting pigs)

The pigs will come from the members and the external support requested concerns mainly:

1.  Support in the acquisition of land (which will also be used in part for banana processing). Financial support will be needed given the still weak financial capacity of the target group,

2.  Acquisition of basic veterinary and concentrated products (working capital),

- Installation of a small artisanal banana processing unit

Bananas are the most consumed fresh fruit in the world. Each year more than 45 million tons of bananas are produced, 96% of which come from developing countries. East Africa is one of the major banana-producing regions with 13.2 million tons per year in 1984-86 (Davies, 1994). This is why the promoters of this project, who have become aware of the problem and the needs of the population in promoting local production, are organizing to set up a company with a view to rational processing of bananas through the application of technology appropriate and new, by eliminating unnecessary intermediaries and this secure income.

Objective of this activity: diversification of revenue sources.

Challenges: how to produce a more stable beer that can be stored for a few weeks.

The necessary support requested is as follows:

1.  Support in the acquisition of co-op specific land. Financial support will be required given the limited financial capacity of the target group,

2.  Construction of an infrastructure for maturation, banana processing,

3. The acquisition of equipment for the processing of bananas: press, maturation drums, packaging for the marketing of banana juice and wine, equipment for the laying of stoppers.

NB:

The by-products will be used to feed pigs, which means that this sub-project will generate zero waste. In addition, some of the peelings will be used to make fertilizers for field fertilization.

6.CHRONOGRAMME

|  | Result | Indicator | Targets | Means of Verification | Chronogramme (year 2022) |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Janv | Févr | Mars | Avr | Mai | Juin | Juil | Août | Sept | Oct | Nov | Déc |
| Impact | Livelihoods of women and youth farm households are improved through increased incomes, improved food and nutrition security, and resilience to climate change | Number of direct households that increased their incomes | 250 | Report before (179), mid-term and end project (250) |  |  |  |  |  |  |  |  |  | X | X | X |
|  |  | Number of indirect households that increased their incomes | 750 | Report before (0), mid-term and end project (750) |  |  |  |  |  |  |  |  |  | X | X | X |
|  |  | Number of households with improved food and nutrition security | 250 | Data of evaluation report |  |  |  |  |  |  |  |  |  | X | X | X |
|  |  | number of households with increased resilience to climate change | 1000 | Data of evaluation report |  |  |  |  |  |  |  |  |  | X | X | X |
| Output | A milling unit is installed and functional | Ensure the installation of the mill and the training of millers |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | A seed storage shed is built and functional | 1 building for the conservation of grain (raw materials: maize, wheat, sorghum, corn plant, sesame) and flour (finished products) | 1 | Hangar reception report/Photos |  |  | X | X | X | X |  |  |  |  |  |  |
|  | The Dushirehamwe cooperative opens a marketing shop for consumer goods | 1 shop open | 1 | 1 functional store/items in sales, turnover, member and non-member services |  |  |  |  |  |  | X | X | X |  |  |  |
|  | A pig cow-calf centre has been set up and generates revenue | 1 pigsty built and put into service with a lot of sows and boars brought by the members: infrastructure and biologic equipment | 1 | A joint pigsty of at least 50 sows and boars at start-up is set up |  |  |  |  |  |  | X | X | X |  |  |  |
|  |  | 1 kit of veterinary products purchased | 1 | 1 starter kit of veterinary products and concentrates is purchased |  |  |  |  |  |  | X | X |  |  |  |  |
|  | A banana juice/wine manufacturing unit has been installed and operational | 1 infrastructure is set up | 1 | 1 single room built for the processing of bananas |  |  |  |  |  |  |  | X | X |  |  |  |
|  |  | Equipment purchased, installed and put into service | 1 | 1 lot of equipment purchased (1 filter press, banana wine maturation drums, buckets, use and packaging cans, staff outfits, and other small wine quality control tools, etc.) |  |  |  |  |  |  |  |  |  | X | X |  |
|  | Capacity-building sessions are held on a variety of themes to strengthen women’s operational capacity | Number of capacity-building sessions organized/number of participants, topics delivered |  | Multi-thematic training series are provided for these women, including action training | X |  |  | X |  |  | X |  |  | X |  |  |
|  | Linking with IMFs was organised and the savings/credit policy developed Linking with IMFs was organised and the savings/credit policy developed | Credits granted to members of the Dushirehamwe cooperative | PM | a relationship with an MFI is organised and at least the cooperative obtains a credit and the Solidarity Guarantee Groups are set up and reinforced (9 GCS obtain credits) |  |  |  | X | X | X |  |  |  |  |  |  |

Project of empowerment of women supported by the Asbl DUSABIKANE/AKARARO.

Location of the project: Municipality Mbuye of the Muramvya Province.

beneficiaries: 187 women supported by DUSABIKANE/AKARARO.

Budget: 78 886   euros

| Budget code | Item | Total in € | Donors | Beneficiaries |
| --- | --- | --- | --- | --- |
| 01 | Investments Production kits in workshop | 17 394 Euros | 15 360 Euros | 2 034 Euros |
| 02 | Project staff fees | 6 305 Euros | 6 305 Euros | 0 |
| 03 | Supply of works, materials and equipment | 44 704 Euros | 38 827 Euros | 5 877 Euros |
| 04 | Travel and transport costs | 5 373 euros | 5 373 Euros | 0 |
| 05 | Other costs | 5 110 euros | 5 110 Euros | 0 |
|  | Total project cost in EUR | 78 886 Euros | 70 975 Euros | 7 911 Euros |

1. Investments Production kits in workshop

| Destination | Items | Estimated cost of kit | Donors | Beneficiaries |
| --- | --- | --- | --- | --- |
| Transformation unit (mill) | Ensure the installation of the mill and the training of millers | 2 564 Euros | 1 801 | 763 |
| Banana juice/wine manufacturing unit | Equipment purchased, installed and put into service; train users | 14 831 Euros | 13 559 | 1 271 |
| TOTAL |  | 17 394 Euros | 15 360 | 2 034 |

2. Project staff fees

| Project staff | Estimated amount | Donors | Beneficiaries |
| --- | --- | --- | --- |
| Project Coordinator | 3 783 Euro | 3 783 Euro | 0 |
| Socio-economist | 2 522 Euro | 2 522 Euro | 0 |
| Total | 6 305 Euros | 6 305 Euros | 0 |

3. Supply of works, materials and equipment

| Description | Estimated amount | Donors | Beneficiaries |
| --- | --- | --- | --- |
| Purchase of raw material and packaging suitable for the manufacture of composite boiled flour | 1 271 Euros | 1 144 | 127 |
| Purchase of corn grains for processing into corn flour for sale in the cooperative’s shop. | 1 271 Euros | 1 144 | 127 |
| 1 building built for the conservation of grain (raw materials: maize, wheat, sorghum, corn plant, sesame) and flour (finished products): (identification of a site, construction of buildings, water supply and electricity) | 19 068 Euros | 17 585 | 1 483 |
| 1 store open (rental agreement, creation of working capital, recruitment of staff, acquisition of goods and items from the shop) | 4 237 Euros | 1 695 | 2 542 |
| 1 pigsty built and put into service with a lot of sows and verrats of departure brought by the members (construction of a pigsty, acquisition of 50 sows and verrats) | 2 119 Euros | 1 560 | 559 |
| 1 kit of veterinary products purchased (veterinary products, pig treatment equipment) | 1 907 Euros | 1 716 | 191 |
| 1 infrastructure set up (identification of a site, construction of buildings, water supply and electricity) | 8 475 Euros | 7 627 | 848 |
| capacity building organized on various themes to strengthen women’s operational capacity | 6 356 Euros | 6 356 | 0 |
| TOTAL | 44 704 Euros | 38 827 Euros | 5 877 Euros |

4. Travel and transport costs

| Description | Estimated costs | Donors | Beneficiaries |
| --- | --- | --- | --- |
| Project staff travel costs (socio-economist) | 1 363 Euros | 1 363 Euros | 0 |
| Travel costs for M&E | 4 010 Euros | 4 010 Euros | 0 |
| TOTAL | 5 373 euros | 5 373 Euros | 0 |

5. Other costs

| Description | Estimated cost | Donors | Beneficiaries |
| --- | --- | --- | --- |
| Communication costs and internet | 1 017 Euros | 1 017 Euros | 0 |
| Office supplies | 1 271 Euros | 1 271 Euros | 0 |
| Payroll taxes for Project staff | 2 022 Euros | 2 022 Euros | 0 |
| Bank charges | 800 Euro | 800 Euros | 0 |
| TOTAL | 5 110 euros | 5 110 Euros | 0 |

***************************************************************************

# Text boxes

PROJECT FOR THE ECONOMIC AND SOCIAL EMPOWERMENT OF WOMEN THROUGH INCOME-GENERATING ACTIVITIES.

WOMEN MEMBERS OF THE DUSHIREHAMWE COOPERATIVE

COMMUNE MBUYE, BURUNDI

Lange Heul, 378 1403 NX Bussum, Pays-Bas

Tél : 003135785000/Mobil : 00619429520

E-mail :snahayo@hotmail.com

N

Ngozi

Kayanza

Kirundo

Muyinga

Karuzi

Muramvya

Cibitoke

Bubanza

Cankuzo

Bujumbura

Mwaro

Gitega

Rutana

Bururi

Ruyigi

Makamba

Lake

Tanganyika

20 0 20 km

1

Municipality Mbuye in Muramvya province

Local production to be manufactured

Manufactured products

Quantity to be  manufactured

The market

Transformation

- They own shop

- other costumers

Of the processing unit

to the cooperative shop